## Dev Plan by release
FTEs
Cycle | New Features | Enhancements/Maintenance | Testing | Documentation | Support/Training | Management | Coordination | Total
0a-ACS 0.x | 1.08 | 0 | 0.36 | 0.36 | 0.3 | 0.1 | 0.2 | 2.4
0b-ACS 1.x | 1.2 |  | 0.4 | 0.4 | 0.6 | 0.1 | 0.2 | 2.9
1-ACS 2.x | 1.5 |  | 0.5 | 0.5 | 1.7 | 0.1 | 0.4 | 4.7
2-ACS 3.x | 1.7045 | 1.3636 | 1.2 | 0.13636 | 1.3 | 0.1 | 0.4 | 6.2045
3-ACS 4.x | 1.8682 | 2.5053 | 0.40909 | 0.27273 | 1.3 | 0.1 | 0.4 | 6.8553
4-ACS 5.x | 0.88636 | 3.8655 | 0.40909 | 0.50455 | 1.8 | 0.1 | 0.5 | 8.0655
5-ACS 6.x | 0.31364 | 3.1427 | 0.68182 | 0.40909 | 1.1409 | 0.1 | 0.5 | 6.2882
6-ACS 7.x | 0.31364 | 3.216 | 0.27273 | 0.34091 | 1.5 | 0.1 | 0.5 | 6.2433
7-ACS 8.x | 0.65455 | 2.4136 | 0.51818 | 0.27273 | 1.5 | 0.1 | 0.5 | 5.9591
Percentage:
Cycle \ % | New Features | Enhancements/Maintenance | Testing | Documentation | Support/Training | Management | Coordination | Total
0a-ACS 0.x | 45 | 0 | 15 | 15 | 12.5 | 4.1667 | 8.3333 | 100
0b-ACS 1.x | 41.3793 | 0 | 13.7931 | 13.7931 | 20.6897 | 3.4483 | 6.8966 | 100
1-ACS 2.x | 31.9149 | 0 | 10.6383 | 10.6383 | 36.1702 | 2.1277 | 8.5106 | 100
2-ACS 3.x | 27.4725 | 21.978 | 19.3407 | 2.1978 | 20.9524 | 1.6117 | 6.4469 | 100
3-ACS 4.x | 27.2518 | 36.5452 | 5.9675 | 3.9784 | 18.9635 | 1.4587 | 5.8349 | 100
4-ACS 5.x | 10.9896 | 47.9261 | 5.0721 | 6.2556 | 22.3174 | 1.2399 | 6.1993 | 100
5-ACS 6.x | 4.9877 | 49.9783 | 10.8429 | 6.5057 | 18.1437 | 1.5903 | 7.9514 | 100
6-ACS 7.x | 5.0236 | 51.5114 | 4.3683 | 5.4604 | 24.0259 | 1.6017 | 8.0086 | 100
7-ACS 8.x | 10.984 | 40.5034 | 8.6957 | 4.5767 | 25.1716 | 1.6781 | 8.3905 | 100
Sum of Days | Rel
Type | 3.1 | Grand Total
1 - New features | 125 | 125
2 - Maintenance | 100 | 100
4 - Documentation | 10 | 10
Grand Total | 235 | 235
Sum of Days | Rel
Type | 4.0 | 4.1 | Grand Total
1 - New features | 137 | 82 | 219
2 - Maintenance | 79 | 57 | 136
3 - Testing | 30 |  | 30
4 - Documentation | 20 |  | 20
Grand Total | 266 | 139 | 405
Sum of Days | Rel
Type | 5.0 | 5.1 | Grand Total
1 - New features | 65 | 102 | 167
2 - Maintenance | 172 | 83 | 255
3 - Testing | 30 | 20 | 50
4 - Documentation | 37 |  | 37
Grand Total | 304 | 205 | 509
Sum of Days | Rel
Type | 6.0 | 6.1 | Grand Total
1 - New features | 23 | 70 | 93
2 - Maintenance | 185 | 72 | 257
3 - Testing |  | 50 | 50
4 - Documentation | 30 | 20 | 50
5 - FBT support | 25 |  | 25
(blank) |  | 0 | 0
Grand Total | 263 | 212 | 475
Sum of Days | Rel
Type | 7.0 | 7.1 | Grand Total
1 - New features | 23 | 80 | 103
2 - Maintenance | 154 | 45 | 199
3 - Testing | 20 |  | 20
4 - Documentation | 25 |  | 25
(blank) |  | 0 | 0
Grand Total | 222 | 125 | 347
Sum of Days | Rel
Type | 8.0 | 8.1 | Grand Total
1 - New features | 48 | 30 | 78
2 - Maintenance | 177 | 40 | 217
3 - Testing | 38 |  | 38
4 - Documentation | 20 |  | 20
(blank) |  | 0 | 0
Grand Total | 283 | 70 | 353

## DPCache_Activities
Activity | Priority | Who | Days | Weeks | 0.0 | Rel | Status | Type
ACS release Integration -1 | 1 - Very High | Chiozzi G. | 10 | 2 | 2 | 5.0 |  | 3 - Testing
ACS release Integration -2 | 1 - Very High | Turolla S. | 10 | 2 | 4 | 5.0 |  | 3 - Testing
ACS Packaging | 1 - Very High | Turolla S. | 10 | 2 | 6 | 5.0 |  | 2 - Maintenance
ACS Packaging | 1 - Very High | Chiozzi G. | 5 | 1 | 7 | 5.0 |  | 2 - Maintenance
ACS Documentation | 1 - Very High | Chiozzi G. | 10 | 2 | 9 | 5.0 |  | 4 - Documentation
ACS Documentation | 1 - Very High | Wang V. | 10 | 2 | 11 | 5.0 |  | 4 - Documentation
GCC 3.4.3 | 1 - Very High | Jeram B. | 5 | 1 | 12 | 5.0 |  | 2 - Maintenance
ACS Command Center extensions | 1 - Very High | Schilling M. | 5 | 1 | 13 | 5.0 |  | 2 - Maintenance
Alarm System - 1 | 1 - Very High | CosyLab | 10 | 2 | 15 | 5.0 |  | 1 - New features
Alarm System - 2 | 1 - Very High | Caproni A. | 20 | 4 | 19 | 5.0 |  | 1 - New features
Bulk Data distributer | 1 - Very High | AOT | 10 | 2 | 21 | 5.0 |  | 1 - New features
Bulk Data documentation | 1 - Very High | AOT | 7 | 1.4 | 22.4 | 5.0 |  | 4 - Documentation
RH Enterprise and Scientific Linux | 1 - Very High | Turolla S. | 5 | 1 | 23.4 | 5.0 |  | 2 - Maintenance
RH Enterprise and Scientific Linux | 1 - Very High | Chiozzi G. | 5 | 1 | 24.4 | 5.0 |  | 2 - Maintenance
Logging: logs in Archive | 1 - Very High | Wang V. | 10 | 2 | 26.4 | 5.0 |  | 1 - New features
Logging: jlog problems | 1 - Very High | Caproni A. | 5 | 1 | 27.4 | 5.0 |  | 2 - Maintenance
Real Time Linux | 1 - Very High | Jeram B. | 5 | 1 | 28.4 | 5.0 |  | 1 - New features
Real Time Linux | 1 - Very High | Turolla S. | 5 | 1 | 29.4 | 5.0 |  | 2 - Maintenance
Component startup and shutdown | 1 - Very High | CosyLab | 10 | 2 | 31.4 | 5.0 |  | 2 - Maintenance
Monitoring data as binary | 2 - High | CosyLab | 5 | 1 | 32.4 | 5.0 |  | 1 - New features
Task Parameters: refactor task classes | 2 - High | Harrington S. | 5 | 1 | 33.4 | 5.0 |  | 2 - Maintenance
Task Parameters: input/output parameter support | 2 - High | Harrington S. | 20 | 4 | 37.4 | 5.0 |  | 2 - Maintenance
Task Parameters: integration of base logger into task structure | 2 - High | Jeram B. | 15 | 3 | 40.4 | 5.0 |  | 2 - Maintenance
Task Parameters: Python shell for tasks | 2 - High | Harrington S. | 20 | 4 | 44.4 | 5.0 |  | 2 - Maintenance
ACS modular tests | 2 - High | Wang V. | 10 | 2 | 46.4 | 5.0 |  | 3 - Testing
Logging: jlog search | 2 - High | Caproni A. | 5 | 1 | 47.4 | 5.0 |  | 2 - Maintenance
Phase out old DBTable classes from BACI and MACI | 2 - High | CosyLab | 10 | 2 | 49.4 | 5.0 |  | 2 - Maintenance
Manager interface to force component release | 2 - High | CosyLab | 3 | 0.6 | 50 | 5.0 |  | 2 - Maintenance
Re-write CDB documentation for APIs and provide code examples | 2 - High | Caproni A. | 10 | 2 | 52 | 5.0 |  | 4 - Documentation
Unload/reload components and their code in Java | 2 - High | Sommer H. | 5 | 1 | 53 | 5.0 |  | 2 - Maintenance
Security: SSH. analysis and prototypes. | 2 - High | Schilling M. | 5 | 1 | 54 | 5.0 |  | 1 - New features
Bulk Data callback error handling | 2 - High | AOT | 3 | 0.6 | 54.6 | 5.0 |  | 2 - Maintenance
Add properties for Float and Float sequences | 2 - High | Jeram B. | 3 | 0.6 | 55.2 | 5.0 |  | 2 - Maintenance
ACS Time base | 2 - High | Fugate D. | 5 | 1 | 56.2 | 5.0 |  | 2 - Maintenance
IDL Simulator extensions | 2 - High | Fugate D. | 10 | 2 | 58.2 | 5.0 |  | 2 - Maintenance
Baci Archive Monitoring | 3 - Normal | Sommer H. | 4 | 0.8 | 59 | 5.0 |  | 2 - Maintenance
Baci Archive Monitoring | 3 - Normal | Fugate D. | 4 | 0.8 | 59.8 | 5.0 |  | 2 - Maintenance
Bulk Data new methods for data transfer without handshaking | 3 - Normal | AOT | 5 | 1 | 60.8 | 5.0 |  | 2 - Maintenance
Event Browser | 3 - Normal | Fugate D. | 10 | 2 | 62.8 | 5.1 |  | 1 - New features
Logging: error trace dialog | 3 - Normal | Caproni A. | 5 | 1 | 63.8 | 5.1 |  | 1 - New features
Jacorb 2.2.2 | 3 - Normal | Schilling M. | 5 | 1 | 64.8 | 5.1 |  | 2 - Maintenance
ACS Benchmarking extensions | 3 - Normal | Fugate D. | 5 | 1 | 65.8 | 5.1 |  | 3 - Testing
JDK update to 1.5 | 3 - Normal | Turolla S. | 2 | 0.4 | 66.2 | 5.1 |  | 2 - Maintenance
JDK update to 1.5 | 3 - Normal | Sommer H. | 5 | 1 | 67.2 | 5.1 |  | 2 - Maintenance
Bulk Data timeout | 4 - Low | AOT | 10 | 2 | 69.2 | 5.1 |  | 2 - Maintenance
Security: Transport Protocol and HTTP. analysis and prototypes | 4 - Low | Schilling M. | 10 | 2 | 71.2 | 5.1 |  | 1 - New features
Notification Channel filtering for structures | 4 - Low | TBD | 0 | 0 | 71.2 | 5.1 |  | 2 - Maintenance
ACS Integration for VxWorks | 4 - Low | Jeram B. | 5 | 1 | 72.2 | 5.1 |  | 2 - Maintenance
Java BACI | 4 - Low | CosyLab | 10 | 2 | 74.2 | 5.1 |  | 1 - New features
ACS Benchmarking coverage | 4 - Low | Fugate D. | 15 | 3 | 77.2 | 5.1 |  | 3 - Testing
Manager federation | 4 - Low | CosyLab | 10 | 2 | 79.2 | 5.1 |  | 1 - New features
Integration of CDB with archive | 4 - Low | Sommer H. | 15 | 3 | 82.2 | 5.1 |  | 1 - New features
Allow dynamic change of logging levels via Container API, Java | 4 - Low | Sommer H. | 5 | 1 | 83.2 | 5.1 |  | 2 - Maintenance
Allow dynamic change of logging levels via Container API, CPP | 4 - Low | CosyLab | 5 | 1 | 84.2 | 5.1 |  | 2 - Maintenance
Java Container shortcutting | 4 - Low | Sommer H. | 5 | 1 | 85.2 | 5.1 |  | 2 - Maintenance
Component code generation from UML | 4 - Low | Harrington S. | 20 | 4 | 89.2 | 5.1 |  | 1 - New features
Restart Service/Component | 5 - Very low | Caproni A. | 7 | 1.4 | 90.6 | 5.1 |  | 2 - Maintenance
Integrate f2py | 5 - Very low | Wang V. | 4 | 0.8 | 91.4 | 5.1 |  | 2 - Maintenance
Task Parameters: OSX port | 5 - Very low | Harrington S. | 20 | 4 | 95.4 | 5.1 |  | 2 - Maintenance
State machine code generator in C++, Java and Python | 5 - Very low | Sommer H. | 17 | 3.4 | 98.8 | 5.1 |  | 1 - New features
BACI:Action Implementator class and design pattern | 5 - Very low | AOT | 10 | 2 | 100.8 | 5.1 |  | 2 - Maintenance
Python baci | 5 - Very low | Fugate D. | 5 | 1 | 101.8 | 5.1 |  | 1 - New features

## DPCache_Activities_2
Activity | Priority | Who | Days | Weeks | 0.0 | Rel | Status | Type | Notes
ACS release Integration -1 | 1 - Very High | GianlucaChiozzi | 10 | 2 | 2 | 7.0 |  | 2 - Maintenance
ACS release Integration -2 | 1 - Very High | StefanoTurolla | 10 | 2 | 4 | 7.0 |  | 2 - Maintenance
ACS Documentation | 1 - Very High | GianlucaChiozzi | 10 | 2 | 6 | 7.0 |  | 4 - Documentation | More people involved
ACS Documentation | 1 - Very High | SteveHarrington | 10 | 2 | 8 | 7.0 |  | 4 - Documentation | More people involved
Porting to JDK 1.6 | 1 - Very High | TBD | 5 | 1 | 9 | 7.0 |  | 2 - Maintenance | More people involved
Upgrading to Python 2.5 | 1 - Very High | TBD | 15 | 3 | 12 | 7.0 |  | 2 - Maintenance
Alarm system: Real-time implementation | 1 - Very High | TBD | 5 | 1 | 13 | 7.0 |  | 1 - New features
Alarm system: Configuration refactoring | 1 - Very High | TBD | 20 | 4 | 17 | 7.0 |  | 2 - Maintenance | More people involved
Performance tests | 1 - Very High | TBD | 20 | 4 | 21 | 7.0 |  | 3 - Testing
Logging: Static & Dynamic configuration at component level | 1 - Very High | TBD | 15 | 3 | 24 | 7.0 |  | 2 - Maintenance | Done
Logging: Binary logging | 1 - Very High | TBD | 10 | 2 | 26 | 7.0 |  | 2 - Maintenance
Logging: Dynamically set default logger levels in Python | 1 - Very High | TBD | 3 | 0.6 | 26.6 | 7.0 |  | 2 - Maintenance | Also GianlucaChiozzi
Logging: Repeat guard implementation for Java | 1 - Very High | TBD | 5 | 1 | 27.6 | 7.0 |  | 2 - Maintenance | Also GianlucaChiozzi
Logging: error trace dialog (viewed jointly e.g. in jlog) | 1 - Very High | TBD | 0 | 0 | 27.6 | 7.0 |  | 2 - Maintenance | More people involved
Investigate Multi Threading and Multi Processor issues | 1 - Very High | TBD | 5 | 1 | 28.6 | 7.0 |  | 2 - Maintenance
Remove deprecated APIs | 1 - Very High | TBD | 10 | 2 | 30.6 | 7.0 |  | 2 - Maintenance | More people involved
FBT support: TMCDB Deployment | 1 - Very High | TBD | 15 | 3 | 33.6 | 7.0 |  | 1 - New features
ACS Security, firewall and http tunneling | 1 - Very High | TBD | 3 | 0.6 | 34.2 | 7.0 |  | 1 - New features
MACI IDL refactoring and cleanup. | 1 - Very High | TBD | 10 | 2 | 36.2 | 7.0 |  | 2 - Maintenance
Upgrade Ant to version 1.7 | 1 - Very High | TBD | 2 | 0.4 | 36.6 | 7.0 |  | 2 - Maintenance
Upgrade to latest version of Xerces | 1 - Very High | TBD | 2 | 0.4 | 37 | 7.0 |  | 2 - Maintenance
Upgrade from RHE 4 update 1 to update 4 or 5 | 1 - Very High | TBD | 10 | 2 | 39 | 7.0 |  | 2 - Maintenance
Automate documentation generation | 1 - Very High | TBD | 5 | 1 | 40 | 7.0 |  | 4 - Documentation
Bulk Data: error back-reporting to suppliers | 1 - Very High | TBD | 10 | 2 | 42 | 7.0 |  | 2 - Maintenance | Some collaboration form StefanoTurolla
Resolve problems too many login attempts at a time. | 1 - Very High | TBD | 3 | 0.6 | 42.6 | 7.0 |  | 2 - Maintenance
Crash recovery: Notify clients when used components come up/go down | 1 - Very High | TBD | 5 | 1 | 43.6 | 7.0 |  | 2 - Maintenance
CASA integration: MICO | 1 - Very High | TBD | 1 | 0.2 | 43.8 | 7.0 |  | 2 - Maintenance
CASA integration: matplotlib | 1 - Very High | TBD | 1 | 0.2 | 44 | 7.0 |  | 2 - Maintenance | +3d HLA
CASA integration; other | 1 - Very High | TBD | 2 | 0.4 | 44.4 | 7.0 |  | 2 - Maintenance
ACS Daemon extensions | 2 - High | TBD | 15 | 3 | 47.4 | 7.1 |  | 1 - New features | 3 days are remaining for this plan. 5 already spent before this plan
Timeout setting for Container, Component and Manager (Java) | 2 - High | TBD | 5 | 1 | 48.4 | 7.1 |  | 2 - Maintenance | Done already
Crash recovery: Make alarms persistent | 2 - High | TBD | 15 | 3 | 51.4 | 7.1 |  | 1 - New features
Crash recovery: Improvement of recovery (stateful vs. stateless components) | 2 - High | TBD | 10 | 2 | 53.4 | 7.1 |  | 1 - New features
Federation of ACS Instances to keep Pipeline and Control on separate, independent sites. | 2 - High | TBD | 15 | 3 | 56.4 | 7.1 |  | 1 - New features
Fix up library dependencies in ACS | 2 - High | TBD | 8 | 1.6 | 58 | 7.1 |  | 2 - Maintenance
Investigation of federation for notification service | 3 - Normal | TBD | 15 | 3 | 61 | 7.1 |  | 1 - New features | +5dArchive
Make exception handling of free text identical in Java, C++, & Python | 3 - Normal | TBD | 5 | 1 | 62 | 7.1 |  | 2 - Maintenance
Alarm system: Python implementation | 3 - Normal | TBD | 10 | 2 | 64 | 7.1 |  | 1 - New features | More people involved
Logging: Query of logging archive from jlog: implicit and transparent | 3 - Normal | TBD | 10 | 2 | 66 | 7.1 |  | 2 - Maintenance
Upgrading to latest ACE/TAO | 3 - Normal | TBD | 10 | 2 | 68 | 7.1 |  | 2 - Maintenance
Investigate ACS on 64bit Linux | 3 - Normal | TBD | 7 | 1.4 | 69.4 | 7.1 |  | 2 - Maintenance | More people involved
| 3 - Normal | TBD | 0 | 0 | 69.4 | 7.1
| 4 - Low | TBD | 0 | 0 | 69.4 | 7.1
| 5 - Very low | TBD | 0 | 0 | 69.4 | 7.1
| 5 - Very low | TBD | 0 | 0 | 69.4 | 7.1
| 5 - Very low | TBD | 0 | 0 | 69.4 | 7.1
| 5 - Very low | TBD | 0 | 0 | 69.4 | 7.1
| 5 - Very low | TBD | 0 | 0 | 69.4 | 7.1
| 5 - Very low | TBD | 0 | 0 | 69.4 | 7.1
| 6 - Not now | TBD | 0 | 0 | 69.4 | 7.1 |  |  | +5d HLA

## DPCache_Activities_3
Activity | Priority | Who | Days | Weeks | 0.0 | Rel | Status | Type | Notes
ACS release Integration -1 | 1 - Very High | GianlucaChiozzi | 10 | 2 | 2 | 6.0 |  | 2 - Maintenance
ACS release Integration -2 | 1 - Very High | StefanoTurolla | 10 | 2 | 4 | 6.0 |  | 2 - Maintenance
ACS Documentation | 1 - Very High | GianlucaChiozzi | 10 | 2 | 6 | 6.0 |  | 4 - Documentation | More people involved
ACS Documentation | 1 - Very High | SteveHarrington | 10 | 2 | 8 | 6.0 |  | 4 - Documentation | More people involved
Alarm System 1st production release, Java and coordination | 1 - Very High | AlessandroCaproni | 15 | 3 | 11 | 6.0 |  | 1 - New features
Jlog connected to ARCHIVE. Part 1 | 1 - Very High | ViolaWang | 9 | 1.8 | 12.8 | 6.0 |  | 2 - Maintenance | +5dArchive
Jlog connected to ARCHIVE. Part 2 | 1 - Very High | AlessandroCaproni | 6 | 1.2 | 14 | 6.0 |  | 2 - Maintenance
Dynamic control of logging levels for Containers: | 1 - Very High | CosyLab | 12 | 2.4 | 16.4 | 6.0 |  | 2 - Maintenance | More people involved
Notification Channel failure handling. Part 1 | 1 - Very High | DavidFugate | 10 | 2 | 18.4 | 6.0 |  | 2 - Maintenance
Notification Channel failure handling. Part 2 | 1 - Very High | BogdanJeram | 10 | 2 | 20.4 | 6.0 |  | 2 - Maintenance
Component Clients that do not prevent Component unloading | 1 - Very High | CosyLab | 10 | 2 | 22.4 | 6.0 |  | 2 - Maintenance
ACS Error System: create standard examples | 1 - Very High | HeikoSommer | 10 | 2 | 24.4 | 6.0 |  | 4 - Documentation | More people involved
ACS Error System: Refactoring of Error System in ACS code | 1 - Very High | BogdanJeram | 20 | 4 | 28.4 | 6.0 |  | 2 - Maintenance | More people involved
Deployment of Components on Nodes and Startup of Containers | 1 - Very High | CosyLab | 20 | 4 | 32.4 | 6.0 |  | 2 - Maintenance
Automatic build of release distributions | 1 - Very High | StefanoTurolla | 10 | 2 | 34.4 | 6.0 |  | 2 - Maintenance | Done
CDB access based on schema specification for dynamic components | 1 - Very High | CosyLab | 10 | 2 | 36.4 | 6.0 |  | 2 - Maintenance
Functional Based Teams: Alarm System applied to scheduling | 1 - Very High | AlessandroCaproni | 10 | 2 | 38.4 | 6.0 |  | 5 - FBT support
Functional Based Teams: Logging cleanup and refactoring in applications | 1 - Very High | AlessandroCaproni | 5 | 1 | 39.4 | 6.0 |  | 5 - FBT support | Also GianlucaChiozzi
Functional Based Teams: Configuration management and CDB configuration | 1 - Very High | HeikoSommer | 10 | 2 | 41.4 | 6.0 |  | 5 - FBT support | Also GianlucaChiozzi
Remove deprecated code | 1 - Very High | CarlitaParedes | 5 | 1 | 42.4 | 6.0 |  | 2 - Maintenance | More people involved
Alarm System 1st production release, CPP | 1 - Very High | SteveHarrington | 5 | 1 | 43.4 | 6.0 |  | 1 - New features
Refactoring of logging in all ACS modules according to new logging guidelines | 1 - Very High | GianlucaChiozzi | 20 | 4 | 47.4 | 6.0 |  | 2 - Maintenance | More people involved
New version of JacORB 2.2.4 | 2 - High | CosyLab | 3 | 0.6 | 48 | 6.0 |  | 2 - Maintenance | 3 days are remaining for this plan. 5 already spent before this plan
Filtering of logging levels in notification service | 2 - High | CosyLab | 10 | 2 | 50 | 6.0 |  | 2 - Maintenance
Refactoring of channels (put logging and monitor archiving in different NS processes) | 2 - High | SteveHarrington | 0 | 0 | 50 | 6.0 |  | 2 - Maintenance | Done already
Implement Loggable base class | 2 - High | GianlucaChiozzi | 3 | 0.6 | 50.6 | 6.0 |  | 1 - New features
Object Explorer, add device/hierarchy oriented navigation tree | 2 - High | CosyLab | 5 | 1 | 51.6 | 6.0 |  | 2 - Maintenance
Timeout settings for Container, Components and Manager (Java) | 2 - High | HeikoSommer | 5 | 1 | 52.6 | 6.0 |  | 2 - Maintenance
ACS additional documentation: Cookbook, BACI, MACI, Architecture | 2 - High | GianlucaChiozzi | 20 | 4 | 56.6 | 6.1 |  | 4 - Documentation
ACS modular tests | 2 - High | SteveHarrington | 15 | 3 | 59.6 | 6.1 |  | 3 - Testing | More people involved
Security: SSH support. Analysis and prototypes | 2 - High | MarcusSchilling | 5 | 1 | 60.6 | 6.1 |  | 1 - New features
ComponentReference template class to hide getComponent | 2 - High | ViolaWang | 5 | 1 | 61.6 | 6.1 |  | 1 - New features
New version of ACE/TAO | 2 - High | BogdanJeram | 10 | 2 | 63.6 | 6.1 |  | 2 - Maintenance | Some collaboration form StefanoTurolla
Bulk Data performance verification | 2 - High | AOT | 15 | 3 | 66.6 | 6.1 |  | 3 - Testing
Bulk Data collection of new requirements and implementation | 2 - High | AOT | 15 | 3 | 69.6 | 6.1 |  | 1 - New features
New version of Python | 3 - Normal | StefanoTurolla | 4 | 0.8 | 70.4 | 6.1 |  | 2 - Maintenance
Logging Error trace popup browser for JLog and applications | 3 - Normal | AlessandroCaproni | 3 | 0.6 | 71 | 6.1 |  | 2 - Maintenance
Object Explorer Collect additional suggestions/requirements | 3 - Normal | GianlucaChiozzi | 2 | 0.4 | 71.4 | 6.1 |  | 2 - Maintenance
Generating ACSDATA from a command | 3 - Normal | StefanoTurolla | 5 | 1 | 72.4 | 6.1 |  | 2 - Maintenance
BACI: phase out old threads | 3 - Normal | ViolaWang | 3 | 0.6 | 73 | 6.1 |  | 2 - Maintenance | +3d HLA
Phase out the old DBTable classes from BACI and MACI. | 3 - Normal | CosyLab | 5 | 1 | 74 | 6.1 |  | 2 - Maintenance
Error Editor | 3 - Normal | Other | 30 | 6 | 80 | 6.1 |  | 1 - New features
Benchmarking extensions discussed in Merano meeting | 3 - Normal | TBD | 5 | 1 | 81 | 6.1 |  | 3 - Testing
ACS Packaging | 4 - Low | StefanoTurolla | 10 | 2 | 83 | 6.1 |  | 2 - Maintenance
ACS Packaging | 4 - Low | GianlucaChiozzi | 5 | 1 | 84 | 6.1 |  | 2 - Maintenance
BACI implementation in python. | 4 - Low | TBD | 15 | 3 | 87 | 6.1 |  | 2 - Maintenance
baciValue refactoring | 4 - Low | TBD | 10 | 2 | 89 | 6.1 |  | 2 - Maintenance
Extend the coverage of performance tests | 4 - Low | TBD | 15 | 3 | 92 | 6.1 |  | 3 - Testing
| 5 - Very low | TBD | 0 | 0 | 92 | 6.1
| 5 - Very low | TBD | 0 | 0 | 92 | 6.1
ACS Time base | 6 - Not now | TBD | 15 | 3 | 95 | 6.1 |  | 1 - New features | +5d HLA

## DPCache_Activities_4
Activity | Priority | Who | Days | Weeks | 0.0 | Rel | Status | Type | Notes
Rework of ALMA interface to notification service | 1 - Very High | HeikoSommer | 15 | 3 | 3 | 8.0 |  | 1 - New features
Port to gcc 4.x | 1 - Very High | BogdanJeram | 15 | 3 | 6 | 8.0 |  | 2 - Maintenance
ACS Security, firewall and http tunneling | 1 - Very High | BogdanJeram | 3 | 0.6 | 6.6 | 8.0 |  | 1 - New features | More people involved
Logging: error trace dialog (viewed jointly e.g. in jlog) | 1 - Very High | AlessandroCaproni | 10 | 2 | 8.6 | 8.0 |  | 2 - Maintenance | More people involved
Python implementation of alarm system API | 1 - Very High | ArneGrimstrup | 10 | 2 | 10.6 | 8.0 |  | 2 - Maintenance | More people involved
MACI IDL refactoring and cleanup. | 1 - Very High | MatejSekoranja | 5 | 1 | 11.6 | 8.0 |  | 2 - Maintenance
Upgrade of Operating System to RH enterprise 5 | 1 - Very High | BogdanJeram | 10 | 2 | 13.6 | 8.0 |  | 2 - Maintenance
jlog enhancements | 1 - Very High | AlessandroCaproni | 20 | 4 | 17.6 | 8.0 |  | 2 - Maintenance
Make alarms persistent | 1 - Very High | AlessandroCaproni | 15 | 3 | 20.6 | 8.0 |  | 2 - Maintenance
Upgrade to latest version of ACE/TAO | 1 - Very High | BogdanJeram | 10 | 2 | 22.6 | 8.0 |  | 2 - Maintenance
ACS release Integration -1 | 1 - Very High | HeikoSommer | 10 | 2 | 24.6 | 8.0 |  | 2 - Maintenance
ACS Documentation | 1 - Very High | JosephSchwarz | 10 | 2 | 26.6 | 8.0 |  | 4 - Documentation | More people involved
Testing on latest update to JDK 1.6 | 1 - Very High | StefanoTurolla | 5 | 1 | 27.6 | 8.0 |  | 3 - Testing
ACS release Integration -2 | 1 - Very High | StefanoTurolla | 10 | 2 | 29.6 | 8.0 |  | 3 - Testing
ACS Documentation | 1 - Very High | HeikoSommer | 10 | 2 | 31.6 | 8.0 |  | 4 - Documentation
Interface repository improvements | 1 - Very High | TBD | 5 | 1 | 32.6 | 8.0 |  | 2 - Maintenance
Make exception handling of free text identical in Java, C++, & Python | 1 - Very High | TBD | 5 | 1 | 33.6 | 8.0 |  | 2 - Maintenance
Implement monitoring component for TMCDB | 1 - Very High | BogdanJeram | 15 | 3 | 36.6 | 8.0 |  | 1 - New features
Performance tests | 1 - Very High | ErikAllaert | 20 | 4 | 40.6 | 8.0 |  | 3 - Testing
Implement monitoring of notification service performance, memory & thread usage | 1 - Very High | BogdanJeram | 15 | 3 | 43.6 | 8.0 |  | 1 - New features
CASA integration: verify continued compatibility with latest release | 2 - High | ArneGrimstrup | 1 | 0.2 | 43.8 | 8.0 |  | 3 - Testing
Maintain/upgrade Python modules | 2 - High | ArneGrimstrup | 2 | 0.4 | 44.2 | 8.0 |  | 2 - Maintenance | w/BogdanJeram
Automate documentation generation | 2 - High | GianlucaChiozzi | 5 | 1 | 45.2 | 8.0 |  | 2 - Maintenance
Bulk Data: error back-reporting to suppliers | 2 - High | RobertoCirami | 20 | 4 | 49.2 | 8.0 |  | 2 - Maintenance
CASA integration; other | 2 – High | TBD | 2 | 0.4 | 49.6 | 8.0 |  | 3 - Testing | +3d HLA
Timeout setting for Container, Component and Manager (Java) | 2 – High | HeikoSommer | 5 | 1 | 50.6 | 8.0 |  | 2 - Maintenance
Crash recovery: Improvement of recovery (stateful vs. stateless components) | 2 – High | HeikoSommer | 10 | 2 | 52.6 | 8.0 |  | 2 - Maintenance | 3 days are remaining for this plan. 5 already spent before this plan
ACS Daemon extensions | 2 – High | MatejSekoranja | 20 | 4 | 56.6 | 8.0 |  | 2 - Maintenance | Done already
Investigation of federation for notification service | 3 - Normal | NicolasTroncoso | 15 | 3 | 59.6 | 8.1 |  | 1 - New features
Fix up library dependencies in ACS | 3 - Normal | BogdanJeram | 8 | 1.6 | 61.2 | 8.1 |  | 2 - Maintenance | More people involved
Investigate Multi Threading and Multi Processor issues | 3 - Normal | BogdanJeram | 15 | 3 | 64.2 | 8.1 |  | 2 - Maintenance
Remove deprecated APIs | 3 - Normal | HeikoSommer | 5 | 1 | 65.2 | 8.1 |  | 2 - Maintenance
Extend pattern type from 32 bits to 64 bits | 3 - Normal | MatejSekoranja | 2 | 0.4 | 65.6 | 8.1 |  | 2 - Maintenance | +5dArchive
Federation of ACS Instances to keep Pipeline and Control on separate, independent sites. | 3 - Normal | TBD | 15 | 3 | 68.6 | 8.1 |  | 1 - New features
Resolve problems too many login attempts at a time. | 3 – Normal | TBD | 3 | 0.6 | 69.2 | 8.1 |  | 2 - Maintenance
Investigate ACS on 64bit Linux | 4 – Low | BogdanJeram | 7 | 1.4 | 70.6 | 8.1 |  | 2 - Maintenance | More people involved
| 5 - Very low | TBD | 0 | 0 | 70.6 | 8.1
| 5 - Very low | TBD | 0 | 0 | 70.6 | 8.1
| 5 - Very low | TBD | 0 | 0 | 70.6 | 8.1
| 5 - Very low | TBD | 0 | 0 | 70.6 | 8.1
| 5 - Very low | TBD | 0 | 0 | 70.6 | 8.1
| 5 - Very low | TBD | 0 | 0 | 70.6 | 8.1
| 6 - Not now | TBD | 0 | 0 | 70.6 | 8.1 |  |  | +5d HLA

## DPCache_Activities_5
Activity | Priority | Who | Days | Weeks | 0.0 | Rel | Type
ACS 3.1 Integration -1 | 1 - Very High | Chiozzi G. | 10 | 2 | 2 | 4.0 | 2 - Maintenance
ACS 3.1 Integration -2 | 1 - Very High | Ibsen J. | 15 | 3 | 5 | 4.0 | 2 - Maintenance
ACS Packaging | 1 - Very High | Harrington S. | 20 | 4 | 9 | 4.0 | 2 - Maintenance
ACS Documentation | 1 - Very High | Chiozzi G. | 10 | 2 | 11 | 4.0 | 4 - Documentation
ACS Documentation | 1 - Very High | Ibsen J. | 10 | 2 | 13 | 4.0 | 4 - Documentation
ACS Benchmarking | 1 - Very High | Fugate D. | 20 | 4 | 15 | 4.0 | 3 - Testing
ACS modular tests | 1 - Very High | Caproni A. | 10 | 2 | 17 | 4.0 | 3 - Testing
Bulk Data transfer | 1 - Very High | AOT | 30 | 6 | 23 | 4.0 | 1 - New features
Alarm System - 1 | 1 - Very High | CosyLab | 10 | 2 | 19 | 4.0 | 1 - New features
Alarm System - 2 | 1 - Very High | Caproni A. | 10 | 2 | 25 | 4.0 | 1 - New features
Manager federation | 1 - Very High | CosyLab | 15 | 3 | 28 | 4.0 | 1 - New features
Command System | 1 - Very High | Harrington S. | 20 | 4 | 32 | 4.0 | 1 - New features
ACS Executables - 1 | 1 - Very High | Chiozzi G. | 5 | 1 | 33 | 4.0 | 1 - New features
ACS Executables - 2 | 1 - Very High | Bogdan J. | 10 | 2 | 35 | 4.0 | 1 - New features
Generic IDL Simulator | 1 - Very High | Fugate D. | 15 | 3 | 38 | 4.0 | 1 - New features
Re-write acsStartJava to use a better strategy for evaluating the CLASSPATH | 1 - Very High | Sommer H. | 5 | 1 | 39 | 4.0 | 2 - Maintenance
Security: Transport Protocol and SSH. HTP Transport Protocol | 1 - Very High | Schilling M. | 10 | 2 | 41 | 4.0 | 1 - New features
Hierarchical Components | 1 - Very High | Sommer H. | 2 | 0.4 | 39.4 | 4.0 | 1 - New features
GCC 3.4 | 2 - High | Bogdan J. | 5 | 1 | 40.4 | 4.0 | 2 - Maintenance
VoTable libraries | 2 - High | Schilling M. | 5 | 1 | 41.4 | 4.0 | 2 - Maintenance
GMP library | 2 - High | Caproni A. | 3 | 0.6 | 42 | 4.0 | 2 - Maintenance
Cleanup/Completion of CDB: | 2 - High | CosyLab | 2 | 0.4 | 42.4 | 4.0 | 2 - Maintenance
Real Time Linux | 2 - High | Bogdan J. | 5 | 1 | 43.4 | 4.0 | 2 - Maintenance
Handle ORB Timeouts | 2 - High | Bogdan J. | 4 | 0.8 | 44.2 | 4.0 | 2 - Maintenance
Python and C++ XML Support | 2 - High | Harrington S. | 10 | 2 | 46.2 | 4.0 | 1 - New features
Integration of CDB with archive | 2 - High | Sommer H. | 5 | 1 | 47.2 | 4.0 | 2 - Maintenance
Antenna MOUNT GUI with Abeans 3 | 2 - Normal | Caproni A. | 10 | 2 | 49.2 | 4.1 | 1 - New features
ACS 3.1 Integration for VxWorks | 3 - Normal | Bogdan J. | 5 | 1 | 50.2 | 4.1 | 2 - Maintenance
JacORB 2.x | 3 - Normal | Sommer H. | 3 | 0.6 | 50.8 | 4.1 | 2 - Maintenance
JDK update with NetBeans and Eclipse installation | 3 - Normal | Sommer H. | 3 | 0.6 | 51.4 | 4.1 | 2 - Maintenance
State Machine code generator in Java | 3 - Normal | Sommer H. | 2 | 0.4 | 50.6 | 4.1 | 1 - New features
State Machine code generator in C++ | 3 - Normal | Harrington S. | 10 | 2 | 52.8 | 4.1 | 1 - New features
State Machine code generator in Python | 3 - Normal | Fugate D. | 5 | 1 | 52.4 | 4.1 | 1 - New features
Java BACI | 3 - Normal | CosyLab | 10 | 2 | 54.4 | 4.1 | 1 - New features
Python BACI | 3 - Normal | Fugate D. | 10 | 2 | 56.4 | 4.1 | 1 - New features
Unload/reload components and their code in Java | 3 - Normal | Sommer H. | 5 | 1 | 55.4 | 4.1 | 1 - New features
Unload/reload components and their code in Python | 3 - Normal | Fugate D. | 5 | 1 | 57.4 | 4.1 | 1 - New features
Restart Service/Component | 3 - Normal | Caproni A. | 10 | 2 | 59.4 | 4.1 | 2 - Maintenance
Advanced process/task Management | 4 - Low | CosyLab | 10 | 2 | 61.4 | 4.1 | 2 - Maintenance
Notification Channel config into CDB | 4 - Low | Fugate D. | 3 | 0.6 | 60 | 4.1 | 2 - Maintenance
Java Logging | 4 - Low | Sommer H. | 5 | 1 | 61 | 4.1 | 2 - Maintenance
Java Container shortcutting | 4 - Low | Sommer H. | 5 | 1 | 62 | 4.1 | 1 - New features
Component code generation from UML | 4 - Low | Harrington S. | 20 | 4 | 66 | 4.1 | 1 - New features
Castor update | 5 - Very low | Sommer H. | 5 | 1 | 67 | 4.1 | 2 - Maintenance
BACI:Action Implementator class and design pattern | 5 - Very low | AOT | 10 | 2 | 69 | 4.1 | 2 - Maintenance
Email transport | 5 - Very low | Schilling M. | 3 | 0.6 | 69.6 | 4.1 | 2 - Maintenance
ACS Makefile Restructuring (SE) |  |  |  | 0 | 69.6 | 4.1 | 2 - Maintenance
CVS support for TAGS, module version, installed version (SE) |  |  |  | 0 | 69.6 | 4.1 | 2 - Maintenance
INTLIST (SE) |  |  |  | 0 | 69.6 | 4.1 | 2 - Maintenance
Support for integration of Eclipse and NetBeans (SE) |  |  |  | 0 | 69.6 | 4.1 | 2 - Maintenance

## DPCache_Activities_6
Activity | Priority | Who | Days | Weeks | 0.0 | Rel | Type
ACS 3.1 Integration | 1 - Very High | Chiozzi G. | 20 | 5 | 5 | 3.1 | 2 - Maintenance
ACS 3.1 Integration for VxWorks | 1 - Very High | Jeram B. | 5 | 1 | 6 | 3.1 | 2 - Maintenance
ACS Master Component | 1 - Very High | Sommer H. | 10 | 2 | 8 | 3.1 | 2 - Maintenance
Error System: Python code generator + Completion support in Java | 1 - Very High | Jeram B. | 0 | 0 | 8 | 3.1 | 1 - New features
TICS porting support | 1 - Very High | Fugate D. | 5 | 1 | 9 | 3.1 | 2 - Maintenance
TICS porting support | 1 - Very High | Jeram B. | 3 | 0.6 | 9.6 | 3.1 | 2 - Maintenance
ACS Documentation refactoring | 1 - Very High | Chiozzi G. | 5 | 1 | 10.6 | 3.1 | 4 - Documentation
ACS Documentation refactoring | 1 - Very High | Caproni A. | 5 | 1 | 11.6 | 3.1 | 4 - Documentation
Generic Idl Simulator | 1 - Very High | Fugate D. | 15 | 3 | 14.6 | 3.1 | 1 - New features
Notification Channel Browser | 1 - Very High | Fugate D. | 10 | 2 | 16.6 | 3.1 | 1 - New features
Platforms and operating Systems | 1 - Very High | Jeram B. | 5 | 1 | 17.6 | 3.1 | 2 - Maintenance
RTLINUX DevIO | 1 - Very High | AOT | 5 | 1 | 18.6 | 3.1 | 1 - New features
RTLINUX Logging | 1 - Very High | AOT | 3 | 0.6 | 19.2 | 3.1 | 1 - New features
RTLINUX Makefile | 1 - Very High | Jeram B. | 2 | 0.4 | 19.6 | 3.1 | 1 - New features
RTLINUX packaging and integration | 1 - Very High | Jeram B. | 10 | 2 | 21.6 | 3.1 | 2 - Maintenance
Bulk Data transfer design | 2 - High | Chiozzi G. | 2 | 0.4 | 22 | 3.1 | 1 - New features
Bulk Data Transfer prototype | 2 - High | AOT | 10 | 2 | 24 | 3.1 | 1 - New features
Cleanup/Completion of CDB: | 2 - High | CosyLab | 8 | 1.6 | 25.6 | 3.1 | 2 - Maintenance
Hierarhical Components (passing component handle to manager as client id), notifications | 2 - High | CosyLab | 4 | 0.8 | 26.4 | 3.1 | 2 - Maintenance
Java Container: implement CORBA shortcutting | 2 - High | Sommer H. | 5 | 1 | 27.4 | 3.1 | 1 - New features
New version of ACE/TAO. | 2 - High | Jeram B. | 10 | 2 | 29.4 | 3.1 | 2 - Maintenance
Refactoring of ACS Makefile | 2 - High | Chiozzi G. | 0 | 0 | 29.4 | 3.1 | 2 - Maintenance
Unit conversions for ABeans and Object Explorer | 2 - High | CosyLab | 5 | 1 | 30.4 | 3.1 | 1 - New features
Antenna mount GUI with ABeans 3 | 2 - High | Caproni A. | 13 | 2.6 | 33 | 3.1 | 1 - New features
Antenna mount GUI with ABeans 3 | 2 - High | CosyLab | 2 | 0.4 | 33.4 | 3.1 | 1 - New features
AcsAlarmSystem | 2 - High | CosyLab | 10 | 2 | 35.4 | 3.1 | 1 - New features
AcsAlarmSystem | 2 - High | AOT | 10 | 2 | 35.4 | 3.1 | 1 - New features
VoTable libraries | 2 - High | Sommer H. | 5 | 1 | 36.4 | 3.1 | 2 - Maintenance
Easy installation of multiple ACS versions and distributions | 2 - High | Chiozzi G. | 0 | 0 | 36.4 | 3.1 | 2 - Maintenance
New version of omniORB and omniORBpy | 2 - High | Fugate D. | 1 | 0.2 | 36.6 | 3.1 | 2 - Maintenance
check ORB timeouts | 2 - High | Fugate D. | 2 | 0.4 | 37 | 3.1 | 2 - Maintenance
ACS Command Center | 3 - Normal | Schilli M. | 10 | 2 | 39 | 3.1 | 1 - New features
New version of JacORB | 3 - Normal | Jeram B. | 2 | 0.4 | 39.4 | 3.1 | 2 - Maintenance
AIPS++ to be integrated | 3 - Normal | Jeram B. | 5 | 1 | 40 | 3.1 | 2 - Maintenance
CppUnit to be included in next patch distribution | 3 - Normal | Chiozzi G. | 0 | 0 | 40 | 3.1 | 2 - Maintenance
Error System: Error Manager | 3 - Normal | AOT | 3 | 0.6 | 40.6 | 3.1 | 1 - New features
FITS library for Java and/or Python. | 3 - Normal | Caproni A. | 5 | 1 | 41.6 | 3.1 | 2 - Maintenance
HTTP and Email transport | 3 - Normal | Schilli M. | 10 | 2 | 43.6 | 3.1 | 1 - New features
Java BACI | 3 - Normal | Caproni A. | 10 | 2 | 45.6 | 3.1 | 1 - New features
Java BACI | 3 - Normal | CosyLab | 20 | 4 | 49.6 | 4.0 | 1 - New features
Restart Service/Component | 3 - Normal | CosyLab | 5 | 1 | 50.6 | 4.0 | 2 - Maintenance
Integration of CDB with archive | 4 - Low | Sommer H. | 5 | 1 | 51.6 | 4.0 | 2 - Maintenance
Notification Channel config into CDB | 4 - Low | Fugate D. | 3 | 0.6 | 52.2 | 4.0 | 2 - Maintenance
Sampling System: Plotting Tool | 4 - Low | AOT | 15 | 3 | 55.2 | 4.0 | 1 - New features
CDB characteristic using SI unit (time in particuar) | 4 - Low | Fugate D. | 5 | 1 | 56.2 | 4.0 | 2 - Maintenance
RTLINUX Notification Channel | 5 - Very Low | Jeram B. | 5 | 1 | 57.2 | 4.0 | 1 - New features
Component Interaction Diagrams | 5 - Very Low | Sommer H. | 10 | 2 | 59.2 | 4.0 | 4 - Documentation
Re-write acsStartJava to use a better strategy for evaluating the CLASSPATH | 5 - Very Low | Sommer H. | 2 | 0.4 | 59.6 | 4.0 | 2 - Maintenance
Value/Remote Object guidelines | 5 - Very Low | Chiozzi G. | 2 | 0.4 | 60 | 4.0 | 4 - Documentation
New version of Castor-xml | 5 - Very Low | Sommer H. | 5 | 1 | 61 | 4.0 | 2 - Maintenance
baci: re-write invokeAction registration mechanism | 5 - Very Low | AOT | 5 | 1 | 62 | 4.0 | 2 - Maintenance
Re-write acsStartContainer and other scripts to better handle order of cmd parms | 5 - Very Low | Fugate D. | 2 | 0.4 | 62.4 | 4.0 | 2 - Maintenance
Advanced process management ("OPUS-like" features) | 6 - Unk | Chiozzi G. | 0 | 0 | 62.4 | 4.0 | 1 - New features
Python XML Support | 6 - Unk | Unassigned | 0 | 0 | 62.4 | 4.0 | 1 - New features